## Sheet1
Test plan
INTRODUCTION
The purpose of this test plan is to ensure the quality, reliability, and security of the online shopping website.
2. TEST OBJECTIVE
Validate the functionality of the website. Ensure the website is user-friendly and meets usability standards. Verify the website's performance under various conditions. Assess the security measures implemented. Confirm compatibility with different browsers and devices.
3. SCOPE
This test plan covers functional, usability, performance, security, and compatibility testing for the online shopping website.
4. TEST SCHEDULE:
START: [Insert Start Date]
End:[ Insert End Date]
5. RESOURCES:
To effectively execute the test plan for an online shopping website, you'll need various resources
Here's a list of resources categorized based on different aspects of the testing process: Test Environment: Devices: Laptops and desktops with different operating systems (Windows, macOS). Tablets (e.g., iPad, Android tablets). Smartphones (e.g., iPhone, Android phones). Browsers: Google Chrome Mozilla Firefox Apple Safari Microsoft Edge Testing Tools: Selenium or similar tools for automated functional testing. JMeter or Gatling for performance testing. OWASP Zap or Burp Suite for security testing. BrowserStack or Sauce Labs for cross-browser testing.
Test Data:
Sample User Data:
Valid and invalid usernames and passwords.
Different user roles (admin, regular user, guest).
Product Data:
A variety of products with different attributes (size, color, price).
Images for products.
Transaction Data:
Test credit card information for payment testing.
TEST CASES:
test cases for each features mentioned in the executive summary.
RISKS:
Integration issues with third-party services. Performance issues under high user loads.
DEPENDENCIES:
Reliance on external services for functionalities like payment processing.
Availability of a stable and representative test environment.
Availability of sufficient and diverse test data.
Completion of UAT by stakeholders.
APPROACH:
Develop a comprehensive test plan that outlines the testing scope, objectives, resources, schedule, and deliverables.
Requirement Traceability Matrix (RTM)
Requirement ID | Requirement Description | Test Scenario ID | Test Case ID | Test Status | Defect ID
REQ-001 | User should be able to register a new account | TS-001 | TC-001 | Passed | -
REQ-002 | User should be able to log in with valid credentials | TS-001 | TC-002 | Passed | -
REQ-003 | User should receive a confirmation email upon registration | TS-002 | TC-003 | Passed | -
REQ-004 | User should be able to browse products | TS-003 | TC-004 | Passed | -
REQ-005 | User should be able to search for a specific product | TS-003 | TC-005 | Passed | -
REQ-006 | User should be able to add products to the shopping cart | TS-004 | TC-006 | Passed | -
REQ-007 | User should be able to view and edit the shopping cart | TS-004 | TC-007 | Passed | -
REQ-008 | User should be able to proceed to checkout | TS-005 | TC-008 | Passed | -
REQ-009 | User should be able to enter shipping and billing information | TS-005 | TC-009 | Passed | -
REQ-010 | User should receive an order confirmation email | TS-006 | TC-010 | Passed | -
REQ-011 | User should be able to view order history | TS-007 | TC-011 | Passed | -
REQ-012 | User should be able to log out | TS-008 | TC-012 | Passed | -
REQ-013 | The website should be compatible with Chrome, Firefox, Safari, and Edge | TS-009 | TC-013 | Passed | -
REQ-014 | The website should be responsive on desktop, tablet, and mobile devices | TS-010 | TC-014 | Passed | -
REQ-015 | Payment information should be securely processed using SSL encryption | TS-011 | TC-015 | Passed | -
TEST CASES:
User Registration:
Test Case 1: Verify User Registration
Objective: To ensure users can successfully register on the website.
Preconditions: User is on the registration page.
Test Steps:
Enter valid details (username, email, password, etc.).
Click on the "Register" button.
Expected Result: User is registered successfully, and a confirmation message is displayed.
DEFECT SHEET:
Defect ID | Date Reported | Reporter | Severity | Priority | Status | Description | Steps to Reproduce | Expected Result | Actual Result | Screenshot | Assigned To | Date Resolved | Resolution
D-001 | 2024-01-25 | Tester A | High | High | Open | Login Failure | 1. Navigate to the login page. 2. Enter valid username and invalid password. 3. Click on the "Login" button. | User should see an error message. | User is redirected to the home page without an error message. | Screenshot | Developer X | - | -
D-002 | 2024-01-26 | Tester B | Medium | Medium | In Progress | Cart Quantity Update | 1. Add a product to the cart. 2. Change the quantity to a negative value. 3. Click on the "Update Cart" button. | The system should display an error message. | The system updates the cart with a negative quantity. | Screenshot | Developer Y | 2024-01-27 | Fixed, pending retest
D-003 | 2024-01-27 | Tester C | Low | Low | Closed | Missing Product Image | 1. Navigate to the product details page. 2. Observe the product image. | Product image should be displayed. | Product image is not displayed. | Screenshot | Developer Z | 2024-01-28 | Image added, closed
D-004 | 2024-01-28 | Tester A | High | High | Assigned | Checkout Process Error | 1. Proceed to checkout. 2. Enter shipping information but leave billing information blank. 3. Confirm the order.
TEST CLOSURE REPORT:
Final Execution of Test Cases:
Ensure that all planned test cases have been executed.
Address any outstanding test cases that were not executed during the testing phase.
Defect Status Review:
Review the status of reported defects.
Verify that reported defects have been resolved and retested, and update their status accordingly.
Test Summary Report:
Prepare a Test Summary Report that provides a comprehensive overview of the testing effort.
Include details such as the number of test cases executed, pass/fail status, defect statistics, and overall test results.
Completion of Test Deliverables:
Confirm that all test deliverables have been completed and are ready for documentation.
Ensure that test artifacts, including test cases, test scripts, and defect reports, are organized and archived appropriately.
Review of Test Objectives and Coverage:
Review whether the test objectives outlined in the test plan have been met.
Assess the coverage of testing in terms of functionality, requirements, and testing types.
User Acceptance Testing (UAT) Feedback:
Gather feedback from stakeholders and end-users who participated in UAT.
Incorporate any relevant feedback into the Test Summary Report.
Lessons Learned Session:
Conduct a lessons learned session with the testing team.
Discuss challenges faced, successes achieved, and areas for improvement in future testing efforts.
Resource Release:
Release testing resources such as test environments, tools, and equipment.
Update resource allocation records accordingly.
Closure of Test Environments:
Close down and document the status of the test environments.
Ensure that all configurations and settings are properly documented for future reference.
Formal Test Closure Meeting:
Conduct a formal test closure meeting with key stakeholders.
Present the Test Summary Report and discuss the overall testing effort and outcomes.
Handover to Production or Next Phase:
If applicable, ensure a smooth handover to the production team or the next phase of the software development life cycle.
Provide necessary documentation and insights for ongoing maintenance and support.
Final Approval and Sign-Off:
Obtain final approval and sign-off from stakeholders, including the project manager and product owner.
Document the formal acceptance of the testing phase.
Archiving and Documentation:
Archive all testing artifacts, including test plans, test cases, and reports.
Ensure that documentation is organized and stored for future reference or audits.
Closure of Test Environment and Tools:
Shut down and document the status of any test environment and testing tools.
Release licenses and resources associated with testing tools.
Feedback and Continuous Improvement:
Encourage team members to provide feedback on the testing process.
Use insights gained to implement continuous improvements in future testing projects.